## Infrastructure
USPS EMS Enablement Guide
Task ID | Task Title | Description | Link | Priority | Resource | Status | Reason | Complete by Date | Dependency Task Code | ENGINEER NOTES
Identity Basics
| What is hybrid identity | Review the hybrd idneitry needs and if needed for enterpise | LINK | INFO ONLY |  | Not Started | Other work load |  |  | Generic Info on Identity
| Five steps to securing your identity infrastructure | If you're reading this document, you're aware of the significance of security. You likely already carry the responsibility for securing your organization. If you need to convince others of the importance of security, send them to read the latest Microsoft Security Intelligence report. This document will help you get a more secure posture using the capabilities of Azure Active Directory by using a five-step checklist to inoculate your organization against cyber-attacks. This checklist will help you quickly deploy critical recommended actions to protect your organization immediately by explaining how to: Strengthen your credentials. Reduce your attack surface area. Automate threat response. Increase your awareness of auditing and monitoring. Enable more predictable and complete end-user security with self-help. | LINK | INFO ONLY |  | Not Started
| What is the identity secure score in Azure Active Directory? | How secure is your Azure AD tenant? If you don't know how to answer this question, read this article to learn how the identity secure score helps you to monitor and improve your identity security posture. What is an identity secure score? The identity secure score is number between 1 and 248 that functions as indicator for how aligned you are with Microsoft's best practices recommendations for security. | LINK | INFO ONLY |  | Not Started
| Microsoft 365 Recommended Identity & Device Configurations | This series of articles describes how to configure secure access to cloud services through Enterprise Mobility + Security products by implementing a recommended environment and configuration, including a prescribed set of conditional access policies and related capabilities. You can use this guidance to protect access to all services that are integrated with Azure Active Directory, including Office 365 services, other SaaS services, and on-premises applications published with Azure AD Application Proxy. | LINK | INFO ONLY |  | Not Started
| Azure AD Data Security Whitepaper | This document explains the following aspects of Azure Active Directory: • Azure AD Components: What are the different components of Azure AD. This will help you to understand the subsequent sections of the document. • Core Data and Location: What customer data is used by Azure AD and where is it located. • Data Protection: How is the directory data protected at transit and at rest. • Data Flow: How data from different sources such as on premises directories and applications flows to and from Azure AD. • Data and Operations: What data and operational procedures are used by the Azure AD engineering team to manage the service. | LINK | INFO ONLY |  | Not Started
| Password Policy Best Practices | This paper provides Microsoft’s recommendations for password management based on current research and lessons from our own experience as one of the largest Identity Providers (IdPs) in the world. It covers recommendations for end users and identity administrators. Microsoft sees over 10 million username/password pair attacks every day. This gives us a unique vantage point to understand the role of passwords in account takeover. The guidance in this paper is scoped to users of Microsoft’s identity platforms (Azure Active Directory, Active Directory, and Microsoft account) though it generalizes to other platforms. | LINK | INFO ONLY |  | Not Started
Azure AD Connect
| Azure AD Connect: Design concepts | The purpose of this document is to describe areas that must be thought through during the implementation design of Azure AD Connect. This document is a deep dive on certain areas and these concepts are briefly described in other documents as well. | LINK | INFO ONLY |  | Not Started
| Topologies for Azure AD Connect | This article describes various on-premises and Azure Active Directory (Azure AD) topologies that use Azure AD Connect sync as the key integration solution. This article includes both supported and unsupported configurations. | LINK | INFO ONLY |  | Not Started
| Azure AD Connect sync: Understand and customize synchronization | The Azure Active Directory Connect synchronization services (Azure AD Connect sync) is a main component of Azure AD Connect. It takes care of all the operations that are related to synchronize identity data between your on-premises environment and Azure AD. Azure AD Connect sync is the successor of DirSync, Azure AD Sync, and Forefront Identity Manager with the Azure Active Directory Connector configured. | LINK | INFO ONLY |  | Not Started |  |  |  | Generic Info on AADC
| Azure AD Connect Installation | Installing Azure AD Connect | LINK | HIGH |  | Not Started |  |  |  | Generic Info on AADC
| Factors influencing the performance of Azure AD Connect | Azure AD Connect syncs your Active Directory to Azure AD. This server is a critical component of moving your user identities to the cloud. | LINK | INFO ONLY |  | Not Started
Password Hash Sync
| How password hash sync works | This article provides information that you need to synchronize your user passwords from an on-premises Active Directory instance to a cloud-based Azure Active Directory (Azure AD) instance. | LINK | INFO ONLY |  | Not Started |  |  |  | Generic on PHS
| Implement password hash synchronization with Azure AD Connect sync | Enable Password hash Sync using Azure AD connect | LINK | HIGH |  | Not Started |  |  |  | Generic on PHS
| Troubleshoot password hash synchronization with Azure AD Connect sync | This topic provides steps for how to troubleshoot issues with password hash synchronization. If passwords are not synchronizing as expected, it can be either for a subset of users or for all users. | LINK | INFO ONLY
Pass Through Authentication
| Azure Active Directory Pass-through Authentication: Quick start | Azure Active Directory (Azure AD) Pass-through Authentication allows your users to sign in to both on-premises and cloud-based applications by using the same passwords. Pass-through Authentication signs users in by validating their passwords directly against on-premises Active Directory. | LINK | INFO ONLY |  | Not Started |  |  |  | Generic Info on OTA
| Azure Active Directory Pass-through Authentication: Current limitations | Azure Active Directory Pass-through Authentication: Current limitations | LINK | INFO ONLY |  | Not Started
ADFS
| Configuring federation with AD FS | Configuring AD FS with Azure AD Connect is simple and only requires a few clicks. The following is required before the configuration. A Windows Server 2012 R2 or later server for the federation server with remote management enabled A Windows Server 2012 R2 or later server for the Web Application Proxy server with remote management enabled An SSL certificate for the federation service name you intend to use (for example sts.contoso.com) | LINK | INFO ONLY |  | Not Started
| Installing the Azure AD Connect Health Agent for AD FS | Installing the Azure AD Connect Health Agent for AD FS | LINK | HIGH |  | Not Started
Seamless Single Sign On
| Azure Active Directory Seamless Single Sign-On | Azure Active Directory Seamless Single Sign-On (Azure AD Seamless SSO) automatically signs users in when they are on their corporate devices connected to your corporate network. When enabled, users don't need to type in their passwords to sign in to Azure AD, and usually, even type in their usernames. This feature provides your users easy access to your cloud-based applications without needing any additional on-premises components. | LINK | INFO ONLY |  | Not Started
| Azure Active Directory Seamless Single Sign-On: Quick start | Deploy Seamless Single Sign-On Azure Active Directory (Azure AD) Seamless Single Sign-On (Seamless SSO) automatically signs in users when they are on their corporate desktops that are connected to your corporate network. Seamless SSO provides your users with easy access to your cloud-based applications without needing any additional on-premises components. | LINK | HIGH |  | Not Started

## Securing Admins
USPS EMS Enablement Guide
Task ID | Task Title | Description | Link | Priority | Resource | Status | Reason | Complete by Date | Dependency Task Code | ENGINEER NOTES
Account Best Practices
| Securing privileged access for hybrid and cloud deployments in Azure AD | The security of most or all business assets in the modern organization depends on the integrity of the privileged accounts that administer and manage IT systems. Malicious actors including cyber-attackers often target admin accounts and other elements of privileged access to attempt to rapidly gain access to sensitive data and systems using credential theft attacks. For cloud services, prevention and response are the joint responsibilities of the cloud service provider and the customer. For more information about the latest threats to endpoints and the cloud, see the Microsoft Security Intelligence Report. This article can help you develop a roadmap toward closing the gaps between your current plans and the guidance described here. | LINK | INFO ONLY |  | Not Started |  |  | Generic info on Security
| Manage emergency-access administrative accounts in Azure AD (BREAK GLASS accounts) | It is important that you prevent being inadvertently locked out of your Azure Active Directory (Azure AD) tenant because you can't sign in or activate an existing individual user's account as an administrator. You can mitigate the impact of inadvertent lack of administrative access by creating two or more emergency access accounts in your tenant. | LINK | INFO ONLY |  | Not Started |  |  | Generic info on Security
| Use non-global administrative roles | Using Azure Active Directory (Azure AD), you can designate separate administrators to serve different functions. Administrators can be designated in the Azure AD portal to perform tasks such as adding or changing users, assigning administrative roles, resetting user passwords, managing user licenses, and managing domain names.The Global Administrator has access to all administrative features. By default, the person who signs up for an Azure subscription is assigned the Global Administrator role for the directory. Only Global Administrators and Privileged Role Administrators can delegate administrator roles. To reduce the risk to your business we recommend that you assign this role to only a few people in your company. | LINK | HIGH |  | Not Started
| Ensure separate user accounts and mail forwarding for global administrator accounts | Ensure separate user accounts and mail forwarding for global administrator accounts Global administrator accounts should not have personal email addresses, as personal email accounts are regularly phished by cyber attackers. To help separate internet risks (phishing attacks, unintentional web browsing) from administrative privileges, create dedicated accounts for each user with administrative privileges. If you have not already done so, create separate accounts for users to perform global admin tasks, to make sure they do not inadvertently open emails or run programs associated with their admin accounts. Be sure those accounts have their email forwarded to a working mailbox. | LINK | HIGH |  | Not Started
| Services Accounts | Best Practices
Azure Multi-Factor Authentication
| Enable MFA baseline Policy for Global Admins | In the last year, identity attacks have increased by 300%. To protect your environment from the ever-increasing attacks, Azure Active Directory (Azure AD) introduces a new feature called baseline protection. Baseline protection is a set of predefined conditional access policies. The goal of these policies is to ensure that you have at least the baseline level of security enabled in all editions of Azure AD. This article provides you with an overview of baseline protection in Azure Active Directory. | LINK | HIGH |  | Not Started |  |  | Recommended action
Identity Protection
| What is Azure Active Directory Identity Protection? | Azure Active Directory Identity Protection is a feature of the Azure AD Premium P2 edition that enables you to: Detect potential vulnerabilities affecting your organization’s identities Configure automated responses to detected suspicious actions that are related to your organization’s identities Investigate suspicious incidents and take appropriate action to resolve them | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on AAIP
| How To: Configure the multi-factor authentication registration policy | Azure AD Identity Protection helps you manage the roll-out of multi-factor authentication (MFA) registration by configuring a policy. This article explains what the policy can be used for an how to configure it. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on AAIP
| How To: Configure the user risk policy | With the user risk, Azure AD detects the probability that a user account has been compromised. As an administrator, you can configure a user risk conditional access policy, to automatically respond to a specific user risk level. This article provides you with the information you need to configure a user risk policy. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on AAIP
| How To: Configure the sign-in risk policy | Azure Active Directory detects risk event types in real-time and offline. Each risk event that has been detected for a sign-in of a user contributes to a logical concept called risky sign-in. A risky sign-in is an indicator for a sign-in attempt that might not have been performed by the legitimate owner of a user account. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on AAIP
Privileged Identity Management
| What is Azure Active Directory Identity Protection? | Azure Active Directory (Azure AD) Privileged Identity Management (PIM) is a service that enables you to manage, control, and monitor access to important resources in your organization. This includes access to resources in Azure AD, Azure resources, and other Microsoft Online Services like Office 365 or Microsoft Intune. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on PIM
| Start using PIM | With Azure Active Directory (Azure AD) Privileged Identity Management (PIM), you can manage, control, and monitor access within your organization. This scope includes access to Azure resources, Azure AD and other Microsoft online services like Office 365 or Microsoft Intune. This article describes how to enable and get started using PIM. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on PIM
| Azure AD roles security wizard in PIM | If you're the first person to run Azure AD Privileged Identity Management (PIM) for your organization, you will be presented with a wizard. The wizard helps you understand the security risks of privileged identities and how to use PIM to reduce those risks. You don't need to make any changes to existing role assignments in the wizard, if you prefer to do it later. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on PIM
| Configure Azure AD directory role settings in PIM | A privileged role administrator can customize Azure AD Privileged Identity Management (PIM) in their organization, including changing the experience for a user who is activating an eligible role assignment. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on PIM
| Configure Azure resource role settings in PIM | When you configure Azure resource role settings, you define the default settings that are applied to Azure resource role assignments in Azure AD Privileged Identity Management (PIM). Use the following procedures to configure the approval workflow and specify who can approve or deny requests. | LINK | INFO ONLY |  | Not Started |  |  | Generic Info on PIM
Hybrid AD Join
| Plan Hybrid Join | In a similar way to a user, a device is becoming another identity you want to protect and also use to protect your resources at any time and location. You can accomplish this goal by bringing your devices' identities to Azure AD using one of the following methods: Azure AD join Hybrid Azure AD join Azure AD registration | LINK | INFO ONLY |  | Not Started
| Control Hybrid Azure Join | Hybrid Azure Active Directory (Azure AD) join is a process to automatically register your on-premises domain-joined devices with Azure AD. There are cases where you don't want all your devices to be registered automatically. This is true, for example, during the initial rollout to verify that everything works as expected. This article provides guidance on how you can control hybrid Azure AD join of your devices. | LINK | INFO ONLY |  | Not Started
| Configure hybrid Azure Active Directory join for federated domains | In this tutorial, you learn how to configure hybrid Azure AD join for devices that federated using ADFS. Configure hybrid Azure AD join Enable Windows down-level devices Verify the registration Troubleshoot | LINK | INFO ONLY |  | Not Started
| Enable Windows down-level devices - Federated | If some of your domain-joined devices are Windows down-level devices, you need to: Update device settings Configure the local intranet settings for device registration Control Windows down-level devices | LINK | INFO ONLY |  | Not Started
| Configure hybrid Azure Active Directory join for managed domains | In this tutorial, you learn how to configure hybrid Azure AD join for devices in managed domains. Configure hybrid Azure AD join Enable Windows down-level devices Verify joined devices Troubleshoot | LINK | INFO ONLY |  | Not Started
| Enable Windows down-level devices - Managed | If some of your domain-joined devices are Windows down-level devices, you need to: Update device settings Configure the local intranet settings for device registration Configure Seamless Single Sign-On (SSO) Control Windows down-level devices | LINK | INFO ONLY |  | Not Started
| Troubleshooting hybrid Azure Active Directory joined Windows 10 and Windows Server 2016 devices | This document provides troubleshooting guidance on how to resolve potential issues. For Windows 10 and Windows Server 2016, hybrid Azure Active Directory join supports the Windows 10 November 2015 Update and above. We recommend using the Anniversary update. | LINK | INFO ONLY |  | Not Started
| Troubleshooting hybrid Azure Active Directory joined down-level devices | This article provides you with troubleshooting guidance on how to resolve potential issues. | LINK | INFO ONLY |  | Not Started
Compliant Device
| Enroll Windows into Intune | This article helps IT administrators simplify Windows enrollment for their users. Once you've set up Intune, users enroll Windows devices by signing in with their work or school account. | LINK | INFO ONLY |  | Not Started
| Enroll Mac into Intune | Intune lets you manage macOS devices to give users access to company email and apps. As an Intune admin, you can set up enrollment for company-owned macOS devices and personally owned macOS devices ("bring your own device" or BYOD). | LINK | INFO ONLY |  | Not Started
| Enroll Android into Intune | As an Intune administrator, you can manage the following Android devices: Android devices, including Samsung Knox Standard devices. Android Enterprise devices, including: Android Enterprise work profile devices: Personal devices granted permission to access corporate data. Admins can manage work accounts, apps, and data. Personal data on the device is kept separate from work data and admins don't control personal settings or data. Android Enterprise dedicated devices: Corporate-owned, single use devices, such as digital signage, ticket printing, or inventory management. Admins lock down the usage of a device for a limited set of apps and web links. It also prevents users from adding other apps or taking other actions on the device. Android Enterprise fully managed devices: Corporate-owned, single user devices used exclusively for work and not personal use. Admins can manage the entire device and enforce policy controls unavailable to work profiles. | LINK | INFO ONLY |  | Not Started
| Enroll IOS into Intune | Intune enables mobile device management (MDM) of iPads and iPhones to give users access to company email and apps. As an Intune admin, you can enable enrollment for iOS devices. You can let users enroll personally owned devices, known as "bring your own device" (BYOD) enrollment. You can also enable enrollment of company-owned devices. | LINK | INFO ONLY |  | Not Started
| Compliance Policy | Many mobile device management (MDM) solutions help protect organizational data by requiring users and devices to meet some requirements. In Intune, this feature is called "compliance policies". Compliance policies define the rules and settings that users and devices must meet to be compliant. When combined with conditional access, administrators can block users and devices that don't meet the rules. | LINK | INFO ONLY |  | Not Started
Azure Active Directory Conditional Access
| What is Conditioanl Access | Security is a top concern for organizations using the cloud. A key aspect of cloud security is identity and access when it comes to managing your cloud resources. In a mobile-first, cloud-first world, users can access your organization's resources using a variety of devices and apps from anywhere. As a result of this, just focusing on who can access a resource is not sufficient anymore. To master the balance between security and productivity, you also need to factor how a resource is accessed into an access control decision. With Azure Active Directory (Azure AD) conditional access, you can address this requirement. Conditional access is a capability of Azure Active Directory. With conditional access, you can implement automated access control decisions for accessing your cloud apps that are based on conditions. | LINK | INFO ONLY |  | Not Started
| Lock Down Admin access with CA - Create CA policy to restrict admin access to Specific locations and Protected devices |  | LINK | INFO ONLY |  | Not Started |  |  | Recommended action

## Protecting Devices
USPS EMS Enablement Guide
Task ID | Task Title | Description | Link | Priority | Resource | Status | Reason | Complete by Date | Dependency Task Code | ENGINEER NOTES
Azure AD Device Management
| What is device management in Azure Active Directory? | In a mobile-first, cloud-first world, Azure Active Directory (Azure AD) enables single sign-on to devices, apps, and services from anywhere. With the proliferation of devices - including Bring Your Own Device (BYOD), IT professionals are faced with two opposing goals: Empower the end users to be productive wherever and whenever Protect the corporate assets at any time | LINK | INFO ONLY |  | Not Started
Azure Active Directory Conditional Access.
| What is Conditioanl Access | Security is a top concern for organizations using the cloud. A key aspect of cloud security is identity and access when it comes to managing your cloud resources. In a mobile-first, cloud-first world, users can access your organization's resources using a variety of devices and apps from anywhere. As a result of this, just focusing on who can access a resource is not sufficient anymore. To master the balance between security and productivity, you also need to factor how a resource is accessed into an access control decision. With Azure Active Directory (Azure AD) conditional access, you can address this requirement. Conditional access is a capability of Azure Active Directory. With conditional access, you can implement automated access control decisions for accessing your cloud apps that are based on conditions. | LINK | INFO ONLY |  | Not Started
Windows 10 - Azure Join (OOBE)
| How to: Plan your Azure AD join implementation | Azure AD join allows you to join devices directly to Azure AD without the need to join to on-premises Active Directory while keeping your users productive and secure. Azure AD join is enterprise-ready for both at-scale and scoped deployments. This article provides you with the information you need to plan your Azure AD join implementation. | LINK | INFO ONLY |  | Not Started
| Enable Windows 10 automatic enrollment | Automatic enrollment lets users enroll their Windows 10 devices in Intune. To enroll, users add their work account to their personally owned devices or join corporate-owned devices to Azure Active Directory. In the background, the device registers and joins Azure Active Directory. Once registered, the device is managed with Intune. | LINK | INFO ONLY |  | Not Started
| Configure device settings | To manage your devices using the Azure portal, your devices need to be either registered or joined to Azure AD. As an administrator, you can fine-tune the process of registering and joining devices by configuring the device settings. We recommend requiring multi-factor authentication when registering a device. | LINK | INFO ONLY |  | Not Started
| Join a new Windows 10 device with Azure AD during a first run | With device management in Azure Active Directory (Azure AD), you can ensure that your users are accessing your resources from devices that meet your standards for security and compliance. For more information, see the introduction to device management in Azure Active Directory. With Windows 10, You can join a new device to Azure AD during the first-run experience (FRX). This enables you to distribute shrink-wrapped devices to your employees or students. | LINK | INFO ONLY |  | Not Started
| Bulk enrollment for Windows devices | As an administrator, you can join large numbers of new Windows devices to Azure Active Directory and Intune. To bulk enroll devices for your Azure AD tenant, you create a provisioning package with the Windows Configuration Designer (WCD) app. Applying the provisioning package to corporate-owned devices joins the devices to your Azure AD tenant and enrolls them for Intune management. Once the package is applied, it's ready for your Azure AD users to log on. | LINK | INFO ONLY |  | Not Started
Windows 7/8/10 - Hybrid AD Join
| Plan Hybrid Join | If you have an on-premises Active Directory environment and you want to join your domain-joined devices to Azure AD, you can accomplish this by configuring hybrid Azure AD joined devices. This article provides you with the related steps to implement a hybrid Azure AD join in your environment. | LINK | INFO ONLY |  | Not Started
| Control Hybrid Azure Join | Hybrid Azure Active Directory (Azure AD) join is a process to automatically register your on-premises domain-joined devices with Azure AD. There are cases where you don't want all your devices to be registered automatically. This is true, for example, during the initial rollout to verify that everything works as expected. | LINK | INFO ONLY |  | Not Started
| Configure hybrid Azure Active Directory join for federated domains | In this tutorial, you learn how to configure hybrid Azure AD join for devices that federated using ADFS. | LINK | INFO ONLY |  | Not Started
| Enable Windows down-level devices - Federated | Enable Windows down-level devices If some of your domain-joined devices are Windows down-level devices, you need to: Update device settings Configure the local intranet settings for device registration Control Windows down-level devices | LINK | INFO ONLY |  | Not Started
| Configure hybrid Azure Active Directory join for managed domains | n this tutorial, you learn how to configure hybrid Azure AD join for devices in managed domains. | LINK | INFO ONLY |  | Not Started
| Enable Windows down-level devices - Managed | Enable Windows down-level devices If some of your domain-joined devices are Windows down-level devices, you need to: Update device settings Configure the local intranet settings for device registration Configure Seamless Single Sign-On (SSO) Control Windows down-level devices | LINK | INFO ONLY |  | Not Started
| Troubleshooting hybrid Azure Active Directory joined Windows 10 and Windows Server 2016 devices | This document provides troubleshooting guidance on how to resolve potential issues. For Windows 10 and Windows Server 2016, hybrid Azure Active Directory join supports the Windows 10 November 2015 Update and above. We recommend using the Anniversary update. | LINK | INFO ONLY |  | Not Started
| Troubleshooting hybrid Azure Active Directory joined down-level devices | This article provides you with troubleshooting guidance on how to resolve potential issues. | LINK | INFO ONLY |  | Not Started
Windows 10/11 - Autopilot
| Overview of Windows Autopilot | Windows Autopilot is a collection of technologies used to set up and pre-configure new devices, getting them ready for productive use. You can also use Windows Autopilot to reset, repurpose and recover devices. This solution enables an IT department to achieve the above with little to no infrastructure to manage, with a process that's easy and simple. | LINK | INFO ONLY |  | Not Started
| Set up an enrollment status page | During device setup using Intune, the Enrollment Status Page displays installation information on the device. Some applications, profiles, and certificates might not be installed by the time a user completes the out-of-box enrollment signs in to the device. An enrollment status page can help users understand the status of their device during device setup. You can create multiple enrollment status page profiles and apply them to different groups. | LINK | INFO ONLY |  | Not Started
| Enroll Windows devices in Intune by using the Windows Autopilot | he Windows Autopilot simplifies enrolling devices in Intune. Building and maintaining customized operating system images is a time-consuming process. You might also spend time applying these custom operating system images to new devices to prepare them for use before giving them to your end users. With Microsoft Intune and Autopilot, you can give new devices to your end users without the need to build, maintain, and apply custom operating system images to the devices. When you use Intune to manage Autopilot devices, you can manage policies, profiles, apps, and more after they're enrolled. For an overview of benefits, scenarios, and prerequisites, see Overview of Windows Autopilot. | LINK | INFO ONLY |  | Not Started
Windows 10/11 - Intune Comanagement
| Verify customer is up-to-date with Configuration Manager and Windows | Customer needs to be on at least Windows 10 1709 and Configuration Manager 1710. Preferrably, they are on the latest release for both products. |  | INFO ONLY |  | Not Started
| Verify customer has configured Hybrid Azure AD Join |  |  | INFO ONLY |  | Not Started
| Run the Comanagement Setup Wizard |  | Link | INFO ONLY |  | Not Started
| Educate customer on available workloads to offload to Intune |  | Link | INFO ONLY |  | Not Started
| Ensure Intune has the necessary policies/profiles created and deployed to users/devices that are Comanaged |  |  | INFO ONLY |  | Not Started
| Switch workloads that customer wants Intune to manage |  |  | INFO ONLY |  | Not Started
Mac
|  | Define and enrolls MAC product sand servcies |  | INFO ONLY |  | Not Started
IOS
|  | Define and enrolls MAC product sand servcies |  | INFO ONLY |  | Not Started
Apple DEP
|  | Define and enrolls MAC product sand servcies |  | INFO ONLY |  | Not Started
Android Enrollment
|  | Define and enrolls MAC product sand servcies |  | INFO ONLY |  | Not Started
Android COSU
|  | Define and enrolls MAC product sand servcies |  | INFO ONLY |  | Not Started

## Protecting Users
USPS EMS Enablement Guide
Task ID | Task Title | Description | Link | Priority | Resource | Status | Reason | Complete by Date | Dependency Task Code | ENGINEER NOTES
Azure Multi-Factor Authentication.
| Azure MFA: How to get Azure MFA and version feature comparison | When it comes to protecting your accounts, two-step verification should be standard across your organization. This feature is especially important for accounts that have privileged access to resources.This comparison table discusses the features that are part of each version of Multi-Factor Authentication. | LINK |  |  | INFO ONLY |  | Not Started
| How Azure MFA Works | The security of two-step verification lies in its layered approach. Compromising multiple authentication factors presents a significant challenge for attackers. Even if an attacker manages to learn the user's password, it is useless without also having possession of the additional authentication method. It works by requiring two or more of the listed authentication methods. | LINK |  |  | INFO ONLY |  | Not Started
| Deploy cloud-based Azure MFA | Your MFA rollout plan should include a pilot deployment followed by deployment waves that are within your support capacity. Begin your rollout by applying your Conditional Access policies to a small group of pilot users. | LINK |  |  | INFO ONLY |  | Not Started
| User and Device Settings | As an administrator, you can manage the following user and device settings: Require users to provide contact methods again Delete app passwords Require MFA on all trusted devices | LINK |  |  | INFO ONLY |  | Not Started
| What are Authentication Methods? | As an administrator, choosing authentication methods for Azure Multi-Factor Authentication and self-service password reset (SSPR) it is recommended that you require users to register multiple authentication methods. When an authentication method is not available for a user, they can choose to authenticate with another method. | LINK |  |  | INFO ONLY |  | Not Started
| Combined MFA + SSPR Registration Experience | Before combined registration, users registered authentication methods for Azure Multi-Factor Authentication and self-service password reset (SSPR) separately. People were confused that similar methods were used for Multi-Factor Authentication and SSPR but they had to register for both features. Now, with combined registration, users can register once and get the benefits of both Multi-Factor Authentication and SSPR. | LINK |  |  | INFO ONLY |  | Not Started
Identity Protection.
[6 empty] | INFO ONLY |  | Not Started
Azure Active Directory Conditional Access.
[6 empty] | INFO ONLY |  | Not Started
Privileged Identity Management
[6 empty] | INFO ONLY |  | Not Started
•MFA End User Adoption Kit |  |  | •https://aka.ms/mfatemplates

## Apps and Data (OneClick)
USPS EMS Enablement Guide
Task ID | Task Title | Description | Link | Priority | Resource | Status | Reason | Complete by Date | Dependency Task Code | ENGINEER NOTES
SaaS Apps with SSO
| Application management with Azure AD | Azure Active Directory (Azure AD) provides secure and seamless access to cloud and on-premises applications. Users can sign in once to access Office 365 and other business applications from Microsoft, software as a service (SaaS) applications, on-premises applications, and line of business (LOB) apps. | LINK |  |  | INFO ONLY |  | Not Started
| Add a gallery application | Azure Active Directory (Azure AD) has a gallery that contains thousands of pre-integrated applications. Some of the applications your organization uses are probably in the gallery. This quickstart uses the Azure portal to add a gallery application to your Azure Active Directory (Azure AD) tenant. | LINK |  |  | INFO ONLY |  | Not Started
| Configure Single Sign On (SSO) | This tutorial uses the Azure portal to configure SAML-based single sign-on for an application with Azure Active Directory (Azure AD). Use this tutorial when an application-specific tutorial isn't available. | LINK |  |  | INFO ONLY |  | Not Started
| Methods for assigning users and groups to an app | This article shows you how to assign users or groups to an application in Azure Active Directory (Azure AD). Users must first be assigned to an application before an administrator can grant them access. | LINK |  |  | INFO ONLY |  | Not Started
| How to configure user provisioning to an Azure AD Gallery Application | User account provisioning is the act of creating, updating, and/or disabling user account records in an application’s local user profile store. Most cloud and SaaS applications store the users role and permissions in their own local user profile store, and presence of such a user record in their local store is required for single sign-on and access to work. | LINK |  |  | INFO ONLY |  | Not Started
| Automate user provisioning and deprovisioning to SaaS apps | Azure Active Directory (Azure AD) lets you automate the creation, maintenance, and removal of user identities in cloud (SaaS) applications such as Dropbox, Salesforce, ServiceNow, and more. | LINK |  |  | INFO ONLY |  | Not Started
App Proxy
| Remote Access to on-premises applications through Azure Active Directory's Application Proxy | Azure Active Directory's Application Proxy provides secure remote access to on-premises web applications. After a single sign-on to Azure AD, users can access both cloud and on-premises applications through an external URL or an internal application portal. | LINK |  |  | INFO ONLY |  | Not Started
| Plan an Azure AD Application Proxy deployment | Azure Active Directory (Azure AD) Application Proxy is a secure and cost-effective remote access solution for on-premises applications. It provides an immediate transition path for “Cloud First” organizations to manage access to legacy on-premises applications that aren’t yet capable of using modern protocols. Application Proxy is recommended for giving remote users access to internal resources. Application Proxy replaces the need for a VPN or reverse proxy for these remote access use cases. | LINK |  |  | INFO ONLY |  | Not Started
| Understanding Azure AD Application Proxy Connectors | Connectors are what make Azure AD Application Proxy possible. Connectors are lightweight agents that sit on-premises and facilitate the outbound connection to the Application Proxy service. | LINK |  |  | INFO ONLY |  | Not Started
| Add an on-premises application for remote access through Application Proxy in Azure Active Directory | This Tutorial: Opens ports for outbound traffic and allows access to specific URLs, Installs the connector on your Windows server and registers it with Application Proxy, Verifies the connector installed and registered correctly, Adds an on-premises application to your Azure AD tenant, Verifies a test user can sign on to the application by using an Azure AD account | LINK |  |  | INFO ONLY |  | Not Started
| Choose and configure a single sign-on method | There are several ways to configure an application for single sign-on. Choosing a single sign-on method depends on how the application is configured for authentication. | LINK |  |  | INFO ONLY |  | Not Started
| Wildcard applications in Azure Active Directory Application Proxy | In Azure Active Directory (Azure AD), configuring a large number of on-premises applications can quickly become unmanageable and introduces unnecessary risks for configuration errors if many of them require the same settings. With Azure AD Application Proxy, you can address this issue by using wildcard application publishing to publish and manage many applications at once | LINK |  |  | INFO ONLY |  | Not Started
MAM / WIP
| What are Intune app protection policies | Microsoft Intune app protection policies help protect your company data and prevent data loss. You can use Intune app protection policies independent of any mobile-device management (MDM) solution. This independence helps you protect your company’s data with or without enrolling devices in a device management solution. By implementing app-level policies, you can restrict access to company resources and keep data within the purview of your IT department. | LINK |  |  | INFO ONLY |  | Not started
| How to create and assign Intune app protection policy | Learn how to create and assign Microsoft Intune app protection policies to your users. This topic also describes how to make changes to existing policies. | LINK |  |  | INFO ONLY |  | Not started
| iOS app protection policy settings | This article describes the app protection policy settings for iOS devices. The policy settings that are described can be configured for an app protection policy on the Settings blade in the Azure portal when you make a new policy. | LINK |  |  | INFO ONLY |  | Not started
| Android app protection policy settings | This article describes the app protection policy settings for Android devices. The policy settings that are described can be configured for an app protection policy on the Settings blade in the Azure portal. | LINK |  |  | INFO ONLY |  | Not started
| What to expect when your iOS app is managed by app protection policies | This topic describes the user experience when using apps with app protection policies applied to. App protection policies are applied only when apps are used in the work context; for example, when the user is accessing apps with a work account or accessing files that are stored in a company OneDrive for business location. | LINK |  |  | INFO ONLY |  | Not started
| What to expect when your Android app is managed by app protection policies | This article describes the user experience for apps with app protection policies. App protection policies are applied only when apps are used in a work context: for example, when the user is accessing apps with a work account or accessing files that are stored in a OneDrive for Business location. | LINK |  |  | INFO ONLY |  | Not started
| Get ready to prepare app protection policies for Windows 10 | Enable mobile application management (MAM) for Windows 10 by setting the MAM provider in Azure AD. Setting a MAM provider in Azure AD allows you to define the enrollment state when creating a new Windows Information Protection (WIP) policy with Intune. | LINK |  |  | INFO ONLY |  | Not Started
| Create and deploy Windows Information Protection (WIP) app protection policy with Intune | You can use app protection policies with Windows 10 apps to protect apps without device enrollment. | LINK |  |  | INFO ONLY |  | Not Started
OLM
| Outlook for iOS and Android in Exchange Online | The Outlook app for iOS and Android is designed to bring together email, calendar, contacts, and other files, enabling users in your organization to do more from their mobile devices. This article provides an overview of the architecture | LINK |  |  | INFO ONLY |  | Not Started
| Setup with Modern Auth | How users with modern authentication-enabled accounts can quickly set up their Outlook for iOS and Android accounts in Exchange Online. | LINK |  |  | INFO ONLY |  | Not Started
| Manage Outlook for iOS and Android in Exchange Online | This article describes best practices for managing mobile devices with Outlook for iOS and Android in Exchange Online. | LINK |  |  | INFO ONLY |  | Not Started
| Secure Outlook for iOS and Android | Outlook for iOS and Android provides users the fast, intuitive email and calendar experience that users expect from a modern mobile app, while being the only app to provide support for the best features of Office 365. Outlook provides the security, privacy, and support you need while protecting corporate data via capabilities such as Azure Active Directory conditional access and Intune app protection policies. | LINK |  |  | INFO ONLY |  | Not Started
| Deploy App Config Settings | How to customize the behavior of Outlook for iOS and Android in your Exchange organization. | LINK |  |  | INFO ONLY |  | Not Started
| Outlook for iOS and Android Roadmap | Online public roadmap for Outlook for iOS and Android and Windows Desktop | LINK |  |  | INFO ONLY |  | Not Started
| Using Hybrid Modern Auth with Outlook for iOS and Android | The following sections provide an overview of the hybrid Modern Authentication architecture, the required pre-requisites for its deployment, and how to securely deploy Outlook for iOS and Android for Exchange on-premises mailboxes. | LINK |  |  | INFO ONLY |  | Not Started
AIP
| What is Azure Information Protection | Azure Information Protection (sometimes referred to as AIP) is a cloud-based solution that helps an organization to classify and optionally, protect its documents and emails by applying labels. | LINK |  |  | INFO ONLY |  | Not Started
| Requirements for Azure Information Protection | Before you deploy Azure Information Protection for your organization, make sure that you have the following prerequisites. | LINK |  |  | INFO ONLY |  | Not Started
| Get Started with Azure Information Protection in the Azure Portal | In this quickstart, you'll add Azure Information Protection to the Azure portal, confirm the protection service is activated, create default labels if you don't already have labels, and view the policy settings for Azure Information Protection. | LINK |  |  | INFO ONLY |  | Not Started
SSO to on prem resources
| How SSO to on-premises resources works on Azure AD joined devices | It is probably not a surprise that an Azure Active Directory (Azure AD) joined device gives you a single sign-on (SSO) experience to your tenant's cloud apps. If your environment has an on-premises Active Directory (AD), you can extend the SSO experience on these devices to it. | LINK

## IT Effeciencies
USPS EMS Enablement Guide
Task ID | Task Title | Description | Link | Priority | Resource | Status | Reason | Complete by Date | Dependency Task Code | ENGINEER NOTES
User provisioning, including licensing
| What is group-based licensing in Azure Active Directory? | Microsoft paid cloud services, such as Office 365, Enterprise Mobility + Security, Dynamics 365, and other similar products, require licenses. These licenses are assigned to each user who needs access to these services. To manage licenses, administrators use one of the management portals (Office or Azure) and PowerShell cmdlets. Azure Active Directory (Azure AD) is the underlying infrastructure that supports identity management for all Microsoft cloud services. Azure AD stores information about license assignment states for users. | LINK | INFO ONLY |  | Not Started
| Assign licenses to users by group membership in Azure Active Director | This article walks you through assigning product licenses to a group of users in Azure Active Directory (Azure AD) and then verifying that they're licensed correctly. | LINK | INFO ONLY |  | Not Started
| Identify and resolve license assignment problems for a group in Azure Active Directory | Group-based licensing in Azure Active Directory (Azure AD) introduces the concept of users in a licensing error state. In this article, we explain the reasons why users might end up in this state. | LINK | INFO ONLY |  | Not Started
| How to add migrate users with individual licenses to groups for licensing | You may have existing licenses deployed to users in the organizations via “direct assignment”; that is, using PowerShell scripts or other tools to assign individual user licenses. Before you begin using group-based licensing to manage licenses in your organization, you can use this migration plan to seamlessly replace existing solutions with group-based licensing. | LINK | INFO ONLY |  | Not Started
| Scenarios, limitations, and known issues using groups to manage licensing in Azure Active Directory | Use the following information and examples to gain a more advanced understanding of Azure Active Directory (Azure AD) group-based licensing. | LINK | INFO ONLY |  | Not Started
|  |  |  | INFO ONLY |  | Not Started
Azure AD Connect Health.
| Why use Azure AD Connect Health? | When with Azure AD, your users are more productive because there's a common identity to access both cloud and on-premises resources. Ensuring the environment is reliable, so that users can access these resources, becomes a challenge. Azure AD Connect Health helps monitor and gain insights into your on-premises identity infrastructure thus ensuring the reliability of this environment. It is as simple as installing an agent on each of your on-premises identity servers. | LINK | INFO ONLY |  | Not Started
| Azure AD Connect Health Agent Installation | This document walks you through installing and configuring the Azure AD Connect Health Agents. | LINK | INFO ONLY |  | Not Started
|  |  |  | INFO ONLY |  | Not Started
Self Service Password Reset (SSPR).
| How it works: Azure AD self-service password reset | How does self-service password reset (SSPR) work? What does that option mean in the interface? Continue reading to find out more about Azure Active Directory (Azure AD) SSPR. | LINK | INFO ONLY |  | Not Started
| How to successfully roll out self-service password reset | To ensure a smooth rollout of the Azure Active directory (Azure AD) self-service password reset (SSPR) functionality, most customers complete the following steps: | LINK | INFO ONLY |  | Not Started
| Deploy password reset without requiring end-user registration | To deploy Azure Active Directory (Azure AD) self-service password reset (SSPR), authentication data needs to be present. Some organizations have their users enter their authentication data themselves. But many organizations prefer to synchronize with data that already exists in Active Directory. The synced data is made available to Azure AD and SSPR without requiring user interaction if you: Properly format the data in your on-premises directory. Configure Azure AD Connect by using the express settings. | LINK | INFO ONLY |  | Not Started
| Register for self-service password reset | As an end user, you can reset your password or unlock your account by yourself if you use Azure Active Directory (Azure AD) self-service password reset (SSPR). Before you can use this functionality, you have to register your authentication methods or confirm the predefined authentication methods that your administrator has populated. | LINK | INFO ONLY |  | Not Started
| Combined security information registration | Before combined registration, users registered authentication methods for Azure Multi-Factor Authentication and self-service password reset (SSPR) separately. People were confused that similar methods were used for Multi-Factor Authentication and SSPR but they had to register for both features. Now, with combined registration, users can register once and get the benefits of both Multi-Factor Authentication and SSPR. | LINK | INFO ONLY |  | Not Started
| What is password writeback? | Having a cloud-based password reset utility is great but most companies still have an on-premises directory where their users exist. How does Microsoft support keeping traditional on-premises Active Directory (AD) in sync with password changes in the cloud? Password writeback is a feature enabled with Azure AD Connect that allows password changes in the cloud to be written back to an existing on-premises directory in real time. | LINK
| How-to: Configure password writeback | To configure and enable password writeback, follow these steps: | LINK | INFO ONLY |  | Not Started
| How to: Enable password reset from Windows 7, 8, and 8.1 | As an administrator you have enabled self-service password reset (SSPR), but users keep calling the helpdesk to reset their password because they can't get to a browser window to access the SSPR portal. For Windows 10 machines, you can enable the "Reset password" link at the logon screen using the tutorial Azure AD password reset from the login screen, the following guidance, will help you to enable Windows 7, 8, and 8.1 users to reset their password using SSPR at the Windows logon screen. | LINK | INFO ONLY |  | Not Started
Automatic user provisioning for pre-integrated SaaS applications as listed in the App integration tutorial list, limited to outbound provisioning only. (SaaS Apps with SSO with User provisioning, including licensing.)
|  |  |  | INFO ONLY |  | Not Started
Customized logon screen, including logo, text and images.
|  |  |  | INFO ONLY |  | Not Started
| Add branding to your organization's Azure Active Directory sign-in page | Use your organization's logo and custom color schemes to provide a consistent look-and-feel on your Azure Active Directory (Azure AD) sign-in pages. Your sign-in pages appear when users sign in to your organization's web-based apps, such as Office 365, which uses Azure AD as your identity provider. | LINK | INFO ONLY |  | Not Started
Self-Service and Dynamic Groups (Groups).
|  |  |  | INFO ONLY |  | Not Started
| Set up self-service group management in Azure Active Directory | You can enable users to create and manage their own security groups or Office 365 groups in Azure Active Directory (Azure AD). The owner of the group can approve or deny membership requests, and can delegate control of group membership. Self-service group management features are not available for mail-enabled security groups or distribution lists. | a | INFO ONLY |  | Not Started
Access Review
|  |  |  | INFO ONLY |  | Not Started
Password Protection (Banned Passwords)
|  |  |  | INFO ONLY |  | Not Started
Secure Score
|  |  |  | INFO ONLY |  | Not Started
Intune Data Warehouse and Powerbi
| Install Azure Active Directory Power BI Content pack | The Power BI content pack for Azure Active Directory (Azure AD) gives you the ability to visualize the reporting data from your environment. You can download the pre-built content pack and use it to report all the activities within your directory using the rich visualization experience that Power BI offers. You can also create your own dashboard and share it easily with anyone in your organization. | LINK | INFO ONLY |  | Not Started
| Use the Microsoft Intune Data Warehouse | Use the Intune Data Warehouse to build reports that provide insight into your enterprise mobile environment. For example, some of the reports include: Trend of users enrolling in Intune so you can optimize your license purchases App and OS versions breakdown so you can review that status of mobile devices Enrollment and device compliance trends so you can smoothly roll out policy updates | LINK | INFO ONLY |  | Not Started

## Lookup
Business Requirements
What are the business outcomes you are expecting from this project? |  | Business Stakeholder
Do you have any regulatory or legal compliance requirements that may impact this project? |  | Business Stakeholder
Are there any blackout periods we need to observe or work around? |  | Business Stakeholder
Are there any maintenance windows that we need to work within? |  | Business Stakeholder
Is there a Change Request (CR) process we need to follow? If so, please provide the process. |  | Business Stakeholder
Are there any SLAs we need to maintain during the project? |  | Business Stakeholder
Are there any additional business constraints we need to be aware of? |  | Business Stakeholder
Are there any time frames that we should be aware of for deployment and to be also considered? |  | Business Stakeholder
Do you have a production license key for Office 365? |  | Business Stakeholder
Risk Management
What is your tolerance for email outages during this project? |  | Business Stakeholder
Internal email unavailable? | Business Stakeholder
Inbound email lost? | Business Stakeholder
How reliable are your ancillary services (network, ISP, etc.) |  | Business Stakeholder
Are there any other risks are you concerned about? |  | Business Stakeholder
Current Environment
Describe the current messaging system (messaging platform, version, architecture, topology). |  | IT/Security/Cloud/Business
Describe the current email backup system and processes. |  | IT/Security/Cloud/Business
Do you have an email queuing service? |  | IT/Security/Cloud/Business
Describe the current archiving system, if any. Will this be required post migration? |  | IT/Security/Cloud/Business
Describe the current journaling system, if any. Will this be required post migration? |  | IT/Security/Cloud/Business
What email access application(s) (names and versions) do you use? |  | IT/Security/Cloud/Business
Do you have appliances that use email (e.g. Multi-function Printer)? |  | IT/Security/Cloud/Business
Do you have any backend applications that use email (websites, monitoring tools, etc.)? |  | IT/Security/Cloud/Business
What software are end users using to access email? |  | IT/Security/Cloud/Business
Do you have any Outlook extensions (e.g. Symantec anti-spam, email classification etc.)? |  | IT/Security/Cloud/Business
Do you have any mail enabled applications (e.g. mail merge, CRM, fax, SMS gateways, etc.)? |  | IT/Security/Cloud/Business
Are PSTs being used? Do they need to be migrated? |  | IT/Security/Cloud/Business
Are you using public folders? |  | IT/Security/Cloud/Business
Are you using resource mailboxes? |  | IT/Security/Cloud/Business
What AD Forest Functional level is in use? |  | IT/Security/Cloud/Business
What AD attributes should be included in DirSync? |  | IT/Security/Cloud/Business
Number of mailboxes |  | IT/Security/Cloud/Business
Largest (Gb) |  | IT/Security/Cloud/Business
Smallest (Gb) |  | IT/Security/Cloud/Business
Average (Gb) |  | IT/Security/Cloud/Business
Describe the current network topology including link type, link speeds and average utilization. |  | IT/Security/Cloud/Business
Are you using email quotas? If so what are they? Do you intend to continue using quotas. |  | IT/Security/Cloud/Business
Do you have an email retention policy? What is it? |  | IT/Security/Cloud/Business
Are you aware that there is no support for backing up deleted message in O365? Is this a concern? |  | IT/Security/Cloud/Business
Any requirement for “legal hold”? |  | IT/Security/Cloud/Business
Are there any external entities that require access to your email system? |  | IT/Security/Cloud/Business
Is there a firewall in place that might prevent connectivity to Exchange Online services? |  | IT/Security/Cloud/Business
Are there any webmail proxy services in place |  | IT/Security/Cloud/Business
Are there any Anti-Virus/Antispam services or appliances in place? |  | IT/Security/Cloud/Business
Is the intention to keep the existing Anti- Virus/Antispam hardware/software in addition to Microsoft Exchange Online Protection? |  | IT/Security/Cloud/Business
What email domain(s) will be migrated? Are additional domains or aliases required? |  | IT/Security/Cloud/Business
Client Management
Client Communications – Who will coordinate them? |  | Ssponsor
What user training will be required? |  | Ssponsor
Who will provide it and when? |  | Ssponsor
Is the end user expected to update their Outlook profile? Mobile phone profile? |  | Ssponsor
Migration
Who controls DNS records (both internal and external)? |  | IT/Security/Cloud
Who is responsible for security certificate generation if required for federation? |  | IT/Security/Cloud
What end user applications will access email post migration? |  | IT/Security/Cloud
Where will the users access email from (location scenarios: office, home, hotel, roaming)? |  | IT/Security/Cloud
What devices, operating system and applications will be supported for email access? |  | IT/Security/Cloud
What is the intended backup strategy? |  | IT/Security/Cloud
How much historical mail will be available/retained in the new system? |  | IT/Security/Cloud
Licenses needed by user accounts. |  | IT/Security/Cloud
The requirement of backups/backup policies |  | IT/Security/Cloud
Network capacity and its suitability for the migration. |  | IT/Security/Cloud
Basic training requirements for end users. |  | IT/Security/Cloud
Name of user mailboxes (shared resources) and their sizes & email addresses. |  | IT/Security/Cloud
Storage locations, client (browser, operating systems, Office applications) versions, and configurations. |  | IT/Security/Cloud
Network settings (DNS hosts, proxy and firewall configuration, internal switches, internet connectivity, intranet sites, and available bandwidth). |  | IT/Security/Cloud
Inventory
User accounts – employee email addresses and login credentials (including former employees) |  | IT/Security/Cloud/Consultant
Mailboxes – make sure to include all mailboxes, together with their number and size |  | IT/Security/Cloud/Consultant
Storage details – the locations of file shares |  | IT/Security/Cloud/Consultant
Client data like versions, configurations, and specifications, including OS, browsers and applications |  | IT/Security/Cloud/Consultant
Communication platforms – collaboration systems and IM systems |  | IT/Security/Cloud/Consultant
Network settings – proxy and firewall settings, DNS hosts, etc. |  | IT/Security/Cloud/Consultant
All application details that you’ve integrated – CRM, HR apps, mail-enabled apps, etc. |  | IT/Security/Cloud/Consultant
Migration type
IMAP migration. Use the Exchange admin center or, alternatively, Exchange Online PowerShell to migrate the content from an IMAP messaging system, including from other email services, e.g., Gmail or Yahoo Mail. |  | Business Stakeholder
Cutover migration. With cutover migration, you migrate all on-premises mailboxes to Office 365 over a few days. This strategy works best if you have up to 150 mailboxes, as there is a risk of poor performance for migrating a larger number of mailboxes. |  | Business Stakeholder
Staged migration. A bit slower migration method, the staged migration lets you migrate batches of on-premises mailboxes to Office 365 or Microsoft 365 over a few weeks or months. |  | Business Stakeholder
Hybrid deployment. A hybrid deployment can work as an intermediate step to a complete move to an Office 365 or Microsoft 365 organization. It enables a feature-rich experience and control with the existing on-premises Exchange organization, the same as the cloud. |  | Business Stakeholder
Third-party migration. Use third-party migration tools if you need specific protocols and approaches for email migrations from specific platforms on particular terms. |  | Business Stakeholder
Configuration
By default, users can work with consumer storage locations such as DropBox, Gsuite and OneDrive (personal) will this be a policy for EXO |  | Business Stakeholder
Do you need to customize email encryption (OME) settings including branding and how are you wanting encryption to carry forward |  | Business Stakeholder
Do you need to have enabled PDF encryption, check automatic decryption options (e.g. download attachments, journal reports). |  | Business Stakeholder
Enabled 'App enforced restrictions' to block attachment download from OWA on unmanaged devices |  | Business Stakeholder
Need default archive mailbox size is 100 GB; this can autoexpand the personal archive up to 1 TB. |  | Business Stakeholder
Need archive mailbox can store older messages, and policies can sweep aged items into the archive automatically. |  | Business Stakeholder
Litigation hold will preserve all mailbox items for eDiscovery (even if deleted) |  | Business Stakeholder
Assessement Tool
User accounts |  | Contractor/IT/Exchange Admin
Mailboxes |  | Contractor/IT/Exchange Admin
Storage details |  | Contractor/IT/Exchange Admin
configurations |  | Contractor/IT/Exchange Admin
Network settings |  | Contractor/IT/Exchange Admin
application Integration |  | Contractor/IT/Exchange Admin
Sizes |  | Contractor/IT/Exchange Admin

## Options (hidden)
Expiration_Date | Status_Options | DeployOrNo | YesOrNo | Reasons
2019-06-30 | Complete | Deploy | Yes | 3rd Party Solution
| Not started | Don't Deploy | No | Customer Resource
Allow_Edits | In progress |  |  | Other work load
Yes | Info only |  | YesNoDontKnow | Test
| N/A |  | Yes | Test 2
|  |  | No | Test 3
EDIT_OPTIONS | Priority_Options |  | I don't know | Test 4
New/Add | HIGH |  |  | Test 5
Remove | LOW |  |  | Test 6
Change | OPTIONAL
Change Link Only | INFO ONLY
WARNING_MESSAGES
Potential blocker: Account team will need to assist with the transition of licenses to a new tenant.
This questionnaire and guidance has an expiration date and shouldn't be started after this date:
The guidance provided here has passed the defined expiration date and may no longer be accurate after this date:

## Steps (hidden)
Azure AD Connect
| Azure AD Connect sync: Understand and customize synchronization | LINK | Generic Info on AADC
| Azure AD Connect Installation | LINK | Generic Info on AADC